## Sheet1
MileStone # | MileStone | Dependancies | Estimated Time /Hr(s) | Person | Description | Done
0 | Getting Started | none | 2 | Both | Understand the file structure and deliverables | yes
1 | Lexer Implemented | 0 | 15 | Ed | Implement Lexer
2 | Parser Implemented | 0 | 15 | Clayton | Implement Parser
3 | Makefile and debugging | 2 & 1 | 5 | Ed & Clayton | Create the Makefile and debugg written code
4 | Translator | 3 | 10 | Ed &Clayton | Create the Translator to python